## Sheet1
sno | resource | alloc type | category
1 | bhanu | dedicated | UI & support
2 | bhargav | temp | backend & followups & support
3 | rajesh | temp | integration & app flow
4 | shekar | temp | UI
5 | srinu | temp | backend
6 | pushpa | temp | UI masters & testing
7 | ramesh | dedicated | UI | create all entities by looking through draw.io
8 | arun | temp | deployments

## Sheet2
sno | module | screen | resource | ui | buffer (30%) | backend |  | hours | module | % | effort | days | end date | start date
1 | oms | oms layout |  | 8 | 2.4 |  |  | 18 | oms | 20 | 96 | 5 | 2023-12-06 | 2023-12-01
2 | oms | orders summary |  | 8 | 2.4 |  |  |  | pps | 60 | 213 | 12 | 2023-12-18 | 2023-12-06
3 | oms | step 2 |  | 6 | 1.8 |  |  |  | cps | 90 | 208 | 12 | 2023-12-30 | 2023-12-18
4 | oms | sizes confirmation |  | 6 | 1.8 |  |  |  | wms | 100 | 140 | 8 | 2024-01-07 | 2023-12-30
5 | oms | rm sku mapping |  | 6 | 1.8
6 | oms | line breakdown |  | 12 | 3.6
7 | oms | rm sku comps mapping |  | 12 | 3.6
8 | oms | other integrations & validations |  | 16 | 4.8
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0 |  |  | effort | 720 |  | 40 |  | sai
12 | pps | pps layout |  | 8 | 2.4 | [7 empty] | rajeswari
13 | pps | po creation |  | 12 | 3.6 |  |  | bhanu | 6 |  |  |  | uma
14 | pps | oq update |  | 16 | 4.8 |  |  | shekar | 4 |  |  |  | manisha
15 | pps | fabric props |  | 12 | 3.6 |  | me/srinu | other - eff | 4 |  |  |  | jaswanth
16 | pps | ratios |  | 24 | 7.2 |  | rajeswari | other - eff | 4 |  |  |  | dileep
17 | pps | markers |  | 8 | 2.4
18 | pps | opversion |  | 16 | 4.8
19 | pps | other integrations & validations |  | 24 | 7.2 |  |  |  | 18
20 | pps | docket generation |  | 12 | 3.6
21 | pps | prints and other barcodes |  | 32 | 9.6
22 |  |  |  |  | 0
23 | cps | cps layout |  | 8 | 2.4
24 | cps | cut planning screen |  | 32 | 9.6
25 | cps | docket material request |  | 16 | 4.8
26 | cps | docket material allocation |  | 8 | 2.4
27 | cps | lay reporting |  | 24 | 7.2
28 | cps | cut reporting |  | 16 | 4.8
29 | cps | prints and other barcodes |  | 40 | 12
30 | cps | dashboard |  | 16 | 4.8
31 | missing | others misc |  | 48 | 14.4
32 | wms | other new screens |  | 60 | 18
33 | user auth |  |  | 48 | 14.4
Formulas:
end date = [start date]+[days]
start date = [end date, row above]